## Sheet1
Upcoming Grants and Deadlines
Grant | Request Amount | Announcement/Info | Match | Date Due
TxCDBG - 2023 | Up to $500K | Local governments or counties | 10% | 2023-04-03
TxCDBG - Downtown Revitalization | Up to $500K | Local governments or counties | % of Request | 2023-05-03
TxCDBG - Colonia | Up to $1Million | Eligible entities with Colonias | % of Request | 2023-04-03
DHS - CyberSecurity Grant |  | State Applies/local would be sub-recipients |  | 2023
TPWD - Local Parks Non-Urban Outdooor Rec | Up to $750K | Apply for funds to continue work of the KC park development | 50% | 2023-08-01
Grant Applications and Grants in Progress
Grant | Progress | Announcement/Info | Match | Date Due
LCRA-Lower Colorado River Authority 2023 | Submitted | Apply $$ for Fire Station gas line, heaters, flooring, kitchen | 20% | 2023-01-31
TDEM - DR 4586 - SSA | Submitted | Apply $$ to write Hazard Mitigation Plan | Up to 25% | 2021-11-05
TxCDBG - Colonia - $775,213.00 - Grant Number CFC21-0306 | In Progress | Pre-Award documents signed and returned | 15200 | 2024
Assistance to Firefighters Grant - Grant Number EMW-2020-FG18907 | In Progress | Federal Award $357,447.62 | 17872.38 | End Aug '23
County Transporation Infrastructure Grant (CTIF) - Grant Number CTIF_02_136 | In Progress | Awarded 2020 $102,594 | 20519 | 2024-07-17
Local Parks Small Communities Rec - TPWD - Grant Number - LP-2022-Kinney County-00063 | In Progress | Splashpad - $100,000.00 | $100K | 2021-10-01
TDEM - DR 4572 - Hurricane Laura | Submitted | Apply $$ to write Hazard Mitigation Plan | up to 25% | 2022-01-15
TxCDBG - Colonia Planning Grant - $460K - Grant Number CFP22-0169 | In Progress | Apply $$ to write Hazard Mitigation Plan | No Match | To be determined
Local Emergency Planning Committee | Awarded | Apply for $$ to write a LEPC Plan $47,083.92 | No Match | 2022-12-02
GLO | Submitted | Apply for $$ to cover match amount for HMPlan | No Match | 2021-12-03
TDEM - DR 4485 Covid Related | Submitted | Generators for Entities - Now on Step 12 | 25% | 2022-06-30
SMART Grant | Submitted Phase 1 | Applied for technology | 25% | 2022-12-01
TxCDBG - 2022 FAST Grant | Up to $750K | Local governments or counties | % of Request | 2022-07-29
USDA Loan/Grant - New Jail/Admin Offices | $15 - $18 Million | Local governments or counties | % of Request | 2022-09-01
Grant(s) Under Closeout Procedures or Completed
Grant | Request Amount | Announcement/Info | Matching | Date Due
LCRA - Lower Colorado River Authority 2021 | $50,000K | Completed - Eligible again in 2023 | 20% | Complete
TxCDBG - 2021 - Street Paving | Disqualified-LMI Svc Area | Prelim Scores updated 8/3/2021
Community Resiliency Program | Disqualified -LMI | Requested funds for Community Center $2.2 Million | No Match | 2022-01-19
USDA Grant - Available Funds | Complete | Build shed for the track loader | 17999 | Complete
Community Resiliency Program | Disqualified -LMI | Requested funds for Ambulance $360,000 | No Match | 2022-01-19
Community Resiliency Program | Disqualified -LMI | Requested funds for Community Park $2.6 million | No Match | 2022-01-19
Office of the Governor CyberSecurity | Not Awarded | $970,000 Total funds requested | No Match | 2022-02-10
Hillcrest Foundation | Not Funded | Requested funds ($300K) for baseball field facility | No Match | 2021-11-20
USDA - Track Loader | Funds Received | Completed - Funds Received |  | Complete
Moody Foundation | Not Invited to Apply | Submitted Preapplication Request for Cemetery Committee | $10K | 2022-10-01
Local Parks Non Urban Outdoor Rec - TPWD | Not Funded | Baseball Park and Concession stand w/restrooms | $375K | 2021-10-01